## Sheet1
Updated | 08.01.19
Meeting | Action No | Owner | Action | Timescale | Update | Status | Date Closed
2017-11-01 | 11/17/01 | Andy Harvey | To distribute latest copy of ‘standing orders’ to all councillors | November | Circulated | Completed
2017-11-01 | 11/17/02 | All | To review and comment back to Andy Harvey no later than a week prior to the next meeting. | Week prior to next meeting |  | Completed
2017-11-01 | 11/17/03 | Trevor Benjamin | To obtain missing monthly County Council reports from Mathew Hicks after the meeting. | Week after | Circulated and published on website | Completed
2017-11-01 | 11/17/04 | Trevor Benjamin | To obtain missing monthly District Council reports from Suzie Morley after the meeting. | Week after | Circulated and published on website | Completed
2017-11-01 | 11/17/05 | Tim Brame | To secure chicken wire to wooden bridge on footpath. | November | Don’t Know | Closed
2017-11-01 | 11/17/06 | Gill Davidson | To update and circulate the Parish Newsletter for review by councillors. | November |  | Completed
2017-11-01 | 11/17/07 | All | All to review Parish Newsletter and give a yes / no to its distribution. | November |  | Completed
2017-11-01 | 11/17/08 | All | To distribute Parish Newsletter once agreed | December | Distributed in July | Completed
2017-11-01 | 11/17/09 | Andy Harvey and Ivan Richardson | To compare notes and both peruse identification of play area land / ownership. | November | Compared | Completed
2017-11-01 | 11/17/10 | Andy Harvey | Dog litter in Baptist play/field but it was felt that although a side of the field is a public footpath it’s not the Parish Councils responsibility as she could choose to fence the play area and the footpath. Action to relay this position back to her. | November | Don’t Know | Closed
2017-11-01 | 11/17/11 | Tim Brame | Encroachment of boundary hedge on the adjacent field. Action to contact Ann to understand the concern. | November | Don’t Know | Closed
2017-11-01 | 11/17/12 | Andy Harvey | We agreed to give the Royal British Legion of £50 cheque as usual this year. Action to check if a cheque has been sent and if not arrange. | November |  | Completed
2017-11-01 | 11/17/13 | Andy Harvey | It was agreed Bus shelter to be inspected and if necessary dismantled and removed. Action to review and decided course of action. Trevor Benjamin offered to help if required. | November | Now propose to sell wood | Completed
2018-01-01 | Finance | Clerk | Clerk to remove from insurance schedule and advise insurers | January 2018. |  | Completed | 29.1.18
2018-01-01 | Reports | Clerk | Send C Cllr Hick's report for December 2017 | January 2018. |  | Completed | 28.01.18
2018-01-01 | Finance | Clerk | Ring-fence £1,000 Locality funding from District Councillor | January 2018. |  | Completed | 28.01.18
2018-01-01 | Finance | all cllrs | Goal posts - decision as to whether or not they should be removed pending play area quotes | January 2018. | Agreed to keep 15.10.18 | Completed | 15.10.18
2018-01-01 | Newsletter/Website | Gill Davison /Trevor Benjamin | Oil discount - Newsletter / website item | January 2018. |  | Completed
2018-01-01 | Finance | Clerk | Standing Orders to be amended for approval at March 2018 meeting | Agenda March 2018 meeting | Circulate all councillors 28.01.18 | Completed
2018-01-01 | Finance | All cllrs & Clerk | Bus shelter to be dismantled and disposed of. Clerk to remove from insurance schedule and advise insurers | January 2018. | Insurers 28.01.18 | Completed
2018-05-01 | Footpath | Clerk | The bridge on the footpath by the Allotments was defective as the plank 3rd row in had sunk. ROW to be notified | July | Reported 23.09.18 - to be chased ready for Jan meeting | Ongoing
2018-05-01 | Footpaths | Ivan Richardson | Cllr Richardson kindly agreed to clear the footpath at the back of the allotments. | July | As discussed at July meeting the path in question is not a public footpath. See new action from July Meeting | Closed | 2018-07-09
2018-05-01 | Chairman’s report | Clerk | dog bin to be installed by The Magpie. Clerk to be informed when installed so that MSDC can be notified to place on their list for emptying on a regular basis. | July | Bin installed and MSDC are emptying | Completed | 10.09.18
2018-05-01 | Fidelity cover | Clerk | The meeting agreed that the cover should be raised to £25,000. Proposed by Cllr Mrs Davison, seconded by Cllr Harvey – all in favour | July |  | Ongoing
2018-05-01 | Standing Order | Clerk | amended orders to be circulated for consideration at July meeting | July | There are now a couple of versions that need to be consolidated. See action from July meeting | Closed | 2018-07-09
2018-05-01 | Certificate of Exemption | Clerk / Trevor Benjamin | Certificate of Exemption: Approved and signed. Original to be sent to external auditors, copy to be placed on the web. Proposed by Cllr Richardson, seconded by Cllr Mrs Davison. | July | Status unclear | Ongoing
2018-05-01 | Village Matters | Ivan Richardson | Grass cutting was discussed and it was agreed that the Cemetery would be included in the contract. Cllr Richardson agreed to contact PGM accordingly | July |  | Completed | 2018-07-09
2018-05-01 | Correspondence | Clerk | Discussion on the provision of flashing signs at each end of the village. Clerk to make enquiries as to the cost etc. Speed Signs to be placed on the July agenda. | July | Covered by new action at July Meeting. | Completed | 2018-07-09
2018-07-01 | County Councillors Report | Sam Baldry | To ask C Cllr Hicks for some money from his budget towards the play area | Sep | Not needed at present 15.10.18 | Closed | 15.10.18
2018-07-01 | Footpaths | Ivan Rischardson | To putting more signs out about fines etc for leaving dog mess, which had had some impact previously, and to give some signs to others to do the same. | Sep | Signs have been put out | Completed | 10.09.18
2018-07-01 | Footpaths | Trevor Benjamin | The path to the rear of the allotments was again discussed but agreed it was not a public footpath so the land owner had no obligation to maintain it. However we agreed to write to the owner to see if they were willing to maintain the path as it has previously been available. Judy Dean to let Trevor have the Owners name and address. |  | Area has been cleared but this is not a public right of way so landowner has no responsibility to clear | Completed | 10.09.18
2018-07-01 | Footpaths | Trevor Benjamin | A dirt bike has been causing a nuisance being ridden on public footpaths and playing field and the the speed of one particular car driving up and down Church Lane.a letter is to be written by the parish council advising about this behaviour and safety concerns. | July |  | Completed | 2018-07-24
2018-07-01 | Parish Newsletter | All | We now have printed copies of the village directory to be distributed as agreed within the next couple of weeks. Ivan Richardson Clockhouse Lane and Lambeth Way Kate Dawson Church Lane Sam Baldly Norwich Road (A140) the Tap to Turnpike (including Mowers Hill Lane, Pains Hill) Trevor Benjamin Norwich Road (A140) from Turnpike to Old Rectory Judy Dean Norwich Road (A140) Old Rectory to Magpie Inn Gill Davison Norwich Road (A140) north of the Magpie inn, Debenham, Mendlesham, Green Rd | July |  | Completed | 2018-07-31
2018-07-01 | Parish Newsletter | Ivan Richardson | to email a copy of the invoice to M Bottomley for cheque to be arranged | July | Cheque issued | Completed | 10.08.18
2018-07-01 | Parish Newsletter | M Bottomley | to arrange a cheque for I Richardson. | Sep | Cheque issued | Completed | 10.08.18
2018-07-01 | Speed Indicator Signs | Trevor Benjamin | To get quotes for speed indicator signs for the village either end of the A140 30 MPH. | Sep | Quotes received, application process has started 15.10.18 | Completed | 15.10.18
2018-07-01 | Pavements | Trevor Benjamin | Concerns were raised about the signs and car blocking aspects of the pavements near the Magpie. Judy Dean agreed to provide pictures and Trevor would follow up with the Highways Authority if they are considered a health risk. | Sep | Ivan reported that when he had a look at the issues later that month he did not feel there was a problem. | Closed | 10.09.18
2018-07-01 | Pavements | Trevor Benjamin | Judy Dean to confirm address of vehicle and T Benjamin to send a letter to the resident asking them to park more considerately. | Sep | Address information not received | Closed | 10.09.18
2018-07-01 | Play Area | Sam Baldry | Baldry to speak with W Brame, also to speak with local businesses about donations/sponsorship. | Sep | Information has been shared | Completed | 10.09.18
2018-07-01 | Play Area | Kate Dawson | to look into where we can apply for grants. | Sep | Kate has info | Completed | 10.09.18
2018-07-01 | Standing Orders | Trevor Benjamin | To consolidate the two versions, to ensure November changes on timescales, the data protection changes and the audit report recommendations. | Sep | Updated version sent out for comment. | Completed | 2018-07-27
2018-07-01 | Audit Report | Trevor Benjamin | There are a number of recommendations in the audit report that we will need to get Marylyn to action on her return, Trevor to discuss them with her. This included the sign off process. | Sep |  | Ongoing
2018-09-01 | Parish Clerk | Trevor Benjamin | To speak to Suffolk Cloud regarding generic email address | Nov | Now have generic email address - clerk@stonhamparvapc.org.uk | Completed | 15.10.18
2018-09-01 | Parish Clerk | Wendy Brame | To contact MSDC and SCC with new updated details for Parish matters | Nov | MSDC and SCC notified | Completed | 15.10.18
2018-09-01 | Parish Clerk | Wendy Brame | To speak to SALC re ongoing situation | Nov | Spoken to and Councillors to deal with in future | Completed | 15.10.18
2018-09-01 | County Cllr Report | Wendy Brame | To obtain info re grit bins | Nov | Info obtained - decided against grit bins 15.10.18 | Completed | 15.10.18
2018-09-01 | Finance | Wendy Brame | To check with bank regarding adding signatories | Nov | Form obtained 15.10.18 | Completed | 15.10.18
2018-09-01 | Finance | Wendy Brame | To contact Chapel and ask for invoices to be sent to her | Nov | No invoices as donation only | Completed | 15.10.18
2018-09-01 | Village Matters | Wendy Brame | To add Grass Cutting to agenda | Nov | Added for meeting 06.11.18 | Completed | 15.10.18
2018-10-01 | Parish Clerk | Trevor Benjamin | Update website with new Parish Clerk details | Nov | Added | Completed | 06.11.18
2018-10-01 | Parish Clerk | Wendy Brame | W Brame to contact Vertas to update Parish Clerk | Nov | Email sent 04.11.18 | Completed | 04.11.18
2018-10-01 | Parish Clerk | Wendy Brame | W Brame to look at courses with SALC | Nov | Course provisionally booked for 23rd + 30th Jan | Ongoing
2018-10-01 | GDPR | All Councillors | To read and feedback Website Policy & Privacy Policy | Nov | Done | Completed | 06.11.18
2018-10-01 | GDPR | Trevor Benjamin | To upload Website Policy & Privacy Policy once agreed | Nov | Added to website | Completed | 06.11.18
2018-10-01 | GDPR | Gill Davison | To look at laptop options | Nov | Options discussed, will order from supplier | Completed | 06.11.18
2018-10-01 | GDPR | Gill Davison | To write Document Retention Policy | Jan |  | Ongoing
2018-10-01 | World War 1 | Gill Davison | To speak to Debenham re mininibus usage | Nov | Change of plan as school doing own remembrance service | Completed | 06.11.18
2018-10-01 | World War 1 | Gill Davison | To create leaflet re service for villagers | Nov | Leaflet delievred | Completed | 06.11.18
2018-10-01 | Speed Indicator Signs | Wendy Brame | To email Cllr Hicks regarding locality funding | Nov | Application to be made once we have a reply from Cllr Hicks | Ongoing
2018-10-01 | Speed Indicator Signs | Trevor Benjamin | To start application process | Jan |  | Ongoing
2018-10-01 | Planning | Gill Davison | To research and speak to local residents re planning application DC/18/04153 | Nov | Application withdrawn | Completed | 06.11.18
2018-10-01 | Planning | Gill Davison | To check Magpie planning consent | Nov | Application checked and planning officer emailed who is monitoring situation | Completed | 06.11.18
2018-10-01 | Finance | Wendy Brame | To complete signatory forms for bank account | Nov |  | Ongoing
2018-10-01 | Correspondence | Wendy Brame | To send apologies to Stowmarket CitA | Nov | Email sent | Completed | 06.11.18
2018-10-01 | Other Business | Trevor Benjamin | To email councillors re change of meeting date | Nov | Email sent | Completed | 06.11.18
2018-11-01 | Reports | Wendy Brame | To email Cllr Morley's October & November report | Dec |  | New
2018-11-01 | Footpath | Trevor Benjamin | To cut bramble back on footpath near Magpie | Dec | Brambles cut back | Completed | 08.01.19
2018-11-01 | GDPR | Gill Davison | To find supplier and will email Parish Clerk so laptop can be purchased | Jan |  | New
2018-11-01 | Grass Cutting | Ivan Richardson | To confirm details of contracts to Clerk once clarified with Vertas | Jan |  | Ongoing
2018-11-01 | Grass Cutting | Wendy Brame | To email Vertas and PMG regarding contracts once above done | Jan |  | Ongoing
2018-11-01 | Finance | Wendy Brame | To send copy invoices to SCC re public footpath cutting | Dec |  | New
2018-11-01 | AOB | Wendy Brame | To type new meeting date list for notice board | Jan |  | New
2018-11-01 | AOB | Wendy Brame | To email planning about mobile home on land near Magpie | Jan |  | New
2018-11-01 | AOB | Wendy Brame | To email Earl Stonham Recorder re newsletter for people in village | Jan |  | New
2019-01-01 | Reports | Wendy Brame | To email Democratic Services re D Cllr Morley as no replies received to emails and no reports received | Mar |  | New
2019-01-01 | Footpaths | Wendy Brame | To email Highways and also include photographs | Mar |  | New
2019-01-01 | Cemetery | Wendy Brame | To email T Benjamin with list of charges then to be put on website. | Mar |  | New
2019-01-01 | Footpaths | Ivan Richardson | To speak to villager who previously offered to help with this regarding a date | Feb |  | New
2019-01-01 | Tree Warden | Andrew Harvey | To investigate procedure for TPO | Mar |  | New
2019-01-01 | Village Sign | Ivan Richardson | To clean and paint sign | Mar |  | New
2019-01-01 | Neighbourhood Development Plan | Trevor Benjamin | To email G Davison to see if she wishes to oversee this. | Mar |  | New
2019-01-01 | Finance | Wendy Brame | To complete precept forms and send to MSDC | Jan |  | New